## Slide 1: Projects
Planning, Execution, Tracking, and Evaluation
IEEE
Dave Foye

## Slide 4: What is Project Management?
Identifying; clarifying goals (Concept and Scope)
Planning and organizing tasks (Plan)
Working a structured framework to help a group work productively (Process)
Use of communication tools to help maintain focus and teamwork
Tracking progress and results

## Slide 5: Why Project Management?
Need is related to complexity
  Multiple people
  Multiple resources (labs, equipment, etc.)
  Multiple tasks – some must precede others
  Multiple decision points – approvals
  Limited funds
  Matching of people/resources to tasks
PLAN ACCORDING TO COMPLEXITY

## Slide 8: The Critical Path
Sometimes task B cannot be started before task A is completed
Other types of constraints – calendar, lags, etc.
What is Critical path – any slippage slips whole project
Helpful to know what tasks are on the critical path
Useful to try to shorten the critical path
Example: Ordering Materials

## Slide 9: Suggested Steps in Project Management
Create a careful definition of the project, with goals, constraints, assumptions
Identify project start/end dates, any mandatory milestones, including reports, signoffs, deliverables, etc.
Determine what processes are required
List constraints – money, equipment availability, holidays, etc.
Identify tasks to be accomplished – high level

## Slide 10: Project Management : The Goals
Identify the concept (what)
Identify all processes (how)
Identify endpoints (when)
Identify measures of success, for whom

## Slide 11: Project Processes
Work Processes- Planning, Concept, Design, Build, Document
Communication processes- meetings, notes, e-mail, phone
Reporting and evaluation processes- who and how
Problem solving processes
Resource management

## Slide 12: What happened?

## Slide 13
Problem
Detection
And Team
Reaction

## Slide 14: Suggested Steps, cont.
Refine detailed task list, dropping/ combining, adding things omitted
Then, for each task in list:
Estimate time
Identify dependencies among tasks- first, last, sequences
Identify resources needed(people, money, parts, etc.); constraints

## Slide 15: Suggested Steps, cont.
Organize task groups roughly by starting date
List dependencies that should or MUST hold
Make a GANTT chart to help see timing and task relationships
Identify the critical path
Identify “task leads”; who will do what

## Slide 16: Suggested Steps, cont.
As project progresses:
Monitor, record progress on all tasks, at least weekly – use “Tracking Gantt Chart”
Pay particular attention to those on critical path
Revise plan as needed to take into account changes, adapt to meet milestones

## Slide 17: The Gantt Chart
List of Tasks on a time line
Estimates of how long each task will take
Important points Marked
Especially Good for groups, and tasks longer than a week
Helps think through planning

## Slide 18: Example Gantt Structure
Design
Build
Test
Calibrate
April
May

## Slide 20: Making a Project a Success
Allow for learning
Evaluate feasibility
Problems- evaluate and re-plan
Facilitate Problem solving processes
Watch Resource management
Keep team together-communicate
Beware of scope creep…

## Slide 22: Management of YOUR Project
With your team members
Create a plan for the entire project
Set milestones for tracking progress
Provide more detail for near-term tasks
Use with your facilitator to report progress and revise/add detail to plan
Assign specific tasks to team members
Revise plan and activities as required to achieve objectives

## Slide 23: Simple Summary Steps
Outline Goal and Concept
Evaluate Feasibility
Set specific goals with team
Detail Plan, Work with Team on Tasks
Start work when everyone understands plan
Evaluate progress, re-plan when needed
Problems? Adapt and re-plan
Succeed with your well planned project!